## Risk Register
Risk Number | Description of the Vulnerability | Systems Affected | Risk of Attempting to Exploit | Risk | Attack Vectors | Blocking Mechanisms | Control Owner | Control Description | Remediation Action | Overall CVSS Score | Severity | 2005 - Pass or Fail | 2005 PWC Exception Number | 2005 Exception Details
1 | Unpatched RDP is exposed to the internet | ALL Windows devices | - Malware injection - Data theft - Ransomware installation | - Unauthorized access to Windows devices - Undetected backdoors installed on Windows devices - Potential to move laterally within the network | - Brute forcing RDP credentials - Exploiting known RDP vulnerabilities | - Network-level firewalls - IDS or IPS - AD ACL |  |  | - Update all network devices with latest patches - Remove all old unsupported hardware - Disable RDP on all devices and configure Cisco, Fortinet, and Palo Alto network firewalls to block inbound/outbound RDP connections - Review list of staff members with remote access privileges and install up-to-date Zscaler on their systems - Provide sufficient training and resources for staff members with Zscaler access | 8.1 | High
2 | Web application is vulnerable to SQL injection | ERP System (Oracle 12c) | - Modification/deletion of database records - Data leak - Exposure of sensitive database records | - Exfiltration of sensitive user data - Potential to gain administrative access to application - Execute arbitrary SQL queries | Manipulating input fields to inject malicious SQL queries | - Server-side input validation - Parameterized queries |  |  | - Enable server-side input validation (ERP database) - Disable client-side input validation (ERP database) | 9.2 | Critical
3 | Default password on Cisco admin portal | Cisco devices | - Malicious configuration changes - Network disruption | - Gain administrative access to Cisco devices and modify critical network configurations - Staging for MITM attacks - Launch network-level attacks | - Log in using default credentials - Brute-force known default passwords | - Change default password at set-up - Enable MFA |  |  | - Change default passwords for all Cisco devices - Follow strong password practices (such as use of long passphrase and mixed punctation) - Enable MFA for Cisco devices OR - Finish phasing out Cisco devices as planned, and apply above remediation to Fortinet Fortigate devices | 8 | High
4 | Apache web server vulnerable to CVE-2019-0211 | Apache web servers (on-prem servers) | - Privilege escalation - Unauthorized access to sensitive files - Potential compromise of on-prem servers and lateral movement in network | - Gain root access - Install malware/backdoors - Access and tamper with critical server files | Exploit vulnerability to run scripts and gain root access | - Apply security updates |  |  | - Apply latest updates for Apache web server - Apply latest patches for web server system's OS | 7.8 | High
5 | Web server is exposing sensitive data | AWS Servers | - Unauthorized access to sensitive server data - Data leak/breach - Violation of privacy regulations | - Extraction of sensitive data, such as PID, passwords, or financial details - Use of exposed data for identity theft | - Directly accessing exposed files/directories - Directory traversal - Use Google Dorks to find exposed content | - Well-implemented file and directory permissions - Routine vulnerability assessments prior to moving code to production |  |  | - Review and adjust file and directory permissions for AWS servers - Perform security audit and comprehensive vulnerability scans to identify exposure points - Review security checks/security scripts in development cycle effectiveness | 7.2 | High
6 | Web application has broken access control | PARS, APOLLO | - Breach of user privacy - Unauthorized manipulation of application code and functionality | - Access restricted features - Modify/delete critical data - Impersonation of other users | - Session hijacking - Lack of authentication/authorization enforcement | - Properly configured access control following least privilege - Network segmentation - Multifactor Authentication |  |  | - Review Microsoft AD configuration and establish RBAC, following least privilege principle - Enable MFA on top of already-existing SSO | 7.8 | High
7 | Oracle WebLogic Server vulnerable to CVE-2020-14882 | ERP System (Oracle 12c) | - Remote code execution - Compromise of affected server - Data theft/manipulation | - Execute arbitrary commands on server - Installation of malicious software | Exploit CVE-2020-14882 vulnerability using crafted HTTP requests | - Apply security updates |  |  | - Apply latest updates for Oracle12c database (ERP system) - Apply latest patches for Linux OS (ERP system) | 9.8 | Critical
8 | Misconfigured cloud storage (AWS security group misconfiguration, lack of access restrictions) | AWS Servers, AWS Cloud Storage, Office 365 applications using cloud storage | - Unauthorized access to sensitive data stored in cloud - Data leak/breach - Violation of privacy regulations | - Access to sensitive cloud data - Modify/delete cloud data | - Directly accessing exposed cloud storage and s3 buckets - Use Google Dorks to find exposed buckets | - Well-configured access controls |  |  | - Review and update access controls, permissions, and configurations on AWS servers, AWS cloud storage, and Office 365 applications | 7.5 | High
9 | Microsoft Exchange Server vulnerable to CVE-2021-26855 | Office 365 Messaging, On-prem Microsoft Exchange Servers | - Remote code execution - Unauthorized access to emails and sensitive info - Data manipulation | - Execute arbitrary code on server - Access user emails and attachments - Access confidential proprietary information | Exploit CVE-2021-26855 using crafted HTTPS requests | - Apply Microsoft patches - VPN |  |  | - Apply Microsoft security patches AND move Exchange servers to inside of VPN, to reject HTTPS requests | 9.1 | Critical